## Overall
Sentral Holdings corporate banking portal (Project Gateway): AI-assisted build and 3-year run
All costs in USD. Cloud: Azure retail list prices in westus3 fetched 2026-09-30, no discounts or reservations. Blue cells are inputs; black cells are formulas; green cells link to other sheets.
Inputs
Input | Value
Days of delivery (working days) | 75
Working days per month | 21
Months of delivery
Hours per month (always-on services) | 730
Delivery start date (optional; dates the epics and sprints) | 2026-08-31
Working days per sprint | 10
Years of run after go-live (3 to 5) | 3
Yearly increase in run costs | 3%
Run years, with the yearly increase
Contingency | 10%
Exchange rate (1 USD = x USD) | 1
Exchange rate for Claude prices (1 USD = x USD) | 1
Delivery team (build)
Role | Day rate (USD) | Employees | Days on delivery | Allocation | Mandays | Cost (USD) | Cited from
Delivery lead |  | 1 |  | 50% |  |  | assumption: AI-assisted delivery team for 31 stories over 75 working days; synthetic portfolio figure, owner request 2026-09-30
Solution architect |  | 1 |  | 50% |  |  | assumption: AI-assisted delivery team for 31 stories over 75 working days; synthetic portfolio figure, owner request 2026-09-30
Full-stack developer |  | 1 |  | 100% |  |  | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md Fluent UI with five screens
Cloud / DevOps engineer |  | 1 |  | 100% |  |  | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-10
Data engineer |  | 1 |  | 100% |  |  | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-6
QA engineer |  | 1 |  | 50% |  |  | assumption: AI-assisted delivery team for 31 stories over 75 working days; synthetic portfolio figure, owner request 2026-09-30
Total
Run support (OPEX): IT support and maintenance after go-live
Role | Day rate (USD) | Mandays per year | Cost per year (USD) | Cited from
Support engineer |  | 60 |  | assumption: L2 support, patching and on-call for the portal; synthetic portfolio figure, owner request 2026-09-30
Cloud / DevOps engineer |  | 30 |  | assumption: AKS, Istio, Kong and Vault upgrades in two regions; synthetic portfolio figure, owner request 2026-09-30
Data engineer |  | 20 |  | assumption: pipeline care and model retraining; synthetic portfolio figure, owner request 2026-09-30
Total
Cost summary
Item | Monthly (USD) | Months in delivery | Delivery cost (USD) | Run months per year | Run cost per year (USD) | Run cost over the horizon (USD) | Total (USD) | From
Dev environment |  |  |  | 12 |  |  |  | Dev sheet
Test environment |  |  |  | 12 |  |  |  | Test sheet
UAT environment |  | 2 |  | 12 |  |  |  | UAT sheet
Prod environment |  | 1 |  | 12 |  |  |  | Prod sheet
Delivery team | [7 empty] | Delivery team table above
Run support (OPEX) | [7 empty] | Run support table above
Recurring run costs | [7 empty] | Run Costs sheet
Other one-off costs | [7 empty] | Other Costs sheet
Claude API usage (actual, API list prices) | [7 empty] | Claude Usage sheet
Subtotal
Contingency
Grand total

## Multi-Year
Multi-year view
In USD. Build is the delivery; each year after go-live carries the run costs, raised by the yearly increase, and the revenue given for it. Years past the horizon (Overall input) show zero. Contingency applies to every cost.
Category | Item | Build | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Revenue |  | 0
Revenue |  | 0
Revenue |  | 0
Cost | Build: delivery team, environments during delivery, one-off costs, Claude usage |  | 0 | 0 | 0 | 0 | 0
Cost | Dev environment (run) | 0
Cost | Test environment (run) | 0
Cost | UAT environment (run) | 0
Cost | Prod environment (run) | 0
Cost | Run support (OPEX) | 0
Cost | Recurring run costs | 0
Contingency | Contingency on every cost
Total revenue
Total costs
Net
Cumulative net
Payback
Return on cost (net / costs)

## Epics
Epics: deliverables, forecast and actual
In USD. Forecast: each epic takes a share of the build in proportion to its planned working days (that share of the delivery team and of the environments during delivery), plus the one-off costs tagged to it and its Claude API budget; dates run the epics one after another from the delivery start date. Actual: enter or keep the actual start and end dates; actual working days, the Claude API actual from the ledger, and team and infra scaled by actual / planned days (same team and rates) unless you enter the timesheet team cost. Blue cells are inputs; add an epic in a spare row.
Epic | Name | Deliverables | Planned days | Planned weeks | Planned start | Planned end | Share of build | Team mandays | Team cost (USD) | Infra cost (USD) | Other costs (USD) | Claude API budget (USD) | Forecast total (USD) | Actual start | Actual end | Actual days | Days variance | Days variance % | Claude API actual (USD) | Actual team cost, timesheets (USD) | Actual total (USD) | Cost variance (USD) | Cited from
1 | Secure platform foundation | 1.1 Terraform resource groups and least-privilege Jenkins identity 1.2 AKS with Node Auto Provisioning, Istio mTLS STRICT and Kong ingress 1.3 Vault with Key Vault auto-unseal and secret-free services 1.4 Parallel microservice image builds with Kaniko on Jenkins agents 1.5 Private endpoints and private DNS for lake, SQL, Key Vault and Event Hubs 1.6 Cost guardrails: Databricks cluster policy and clean terraform destroy | 12 | [8 empty] | 55 |  | 2026-08-31 | 2026-09-16 | [7 empty] | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-10
2 | Treasurer portal and maker-checker payments | 2.1 Entra External ID sign-in and company-scoped sessions 2.2 Row-level security for company isolation with blocked-access logging 2.3 Cash position and liquidity dashboard from the serving schema 2.4 Accounts, balances and transactions 2.5 Payment creation with maker-checker approval and execution 2.6 Portal chrome: region badge, synthetic-data banner and error states | 14 | [8 empty] | 65 |  | 2026-09-17 | [8 empty] | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-4
3 | Ledger events through the medallion lake | 3.1 Seeded synthetic world: companies, payroll cycles, suppliers and planted anomalies 3.2 Outbox relay from the SQL ledger to Event Hubs 3.3 Bronze ingestion from the Event Hubs Kafka endpoint 3.4 Silver and gold Delta transforms with serving-schema write-back 3.5 Behind-the-scenes stage panel | 12 | [8 empty] | 55 | [10 empty] | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-5
4 | Lineage and ML cash intelligence | 4.1 Unity Catalog lineage from gold back to the Event Hubs source 4.2 Cash forecast model tracked in MLflow and registered in Unity Catalog 4.3 Isolation Forest payment anomaly detection 4.4 Batch scoring into forecasts and anomalies tables 4.5 Forecast screen and anomaly flags in the portal | 12 | [8 empty] | 60 | [10 empty] | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-7
5 | Multi-region resilience | 5.1 Region-2 AKS from the same Terraform module 5.2 Front Door origins, health probes and Front Door-only ingress 5.3 SQL failover group behind a Terraform flag 5.4 Grafana requests-per-second by region 5.5 Regional failover drill and runbook | 10 | [8 empty] | 45 | [10 empty] | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-12
6 | Security assurance, UAT and go-live | 6.1 Security controls evidence pack for the CISO review 6.2 PDPA data-protection assessment and penetration test remediation 6.3 UAT with Group Treasury and business sign-off 6.4 CAB approval, production cut-over and hypercare | 15 | [8 empty] | 35 | [10 empty] | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md CAP-14
Total
Formulas:
Planned end = IF([Planned start]="","",WORKDAY([Planned start],[Planned days]-1))
Actual days = IF(OR([Planned days]="",[Actual start]="",[Actual end]=""),"",NETWORKDAYS([Actual start],[Actual end]))
Planned start = IF(OR([Planned days]="",ProjectStart=""),"",WORKDAY([Planned end, row above],1))

## Sprints
Sprints: forecast and actual
In USD. Every sprint is a timebox of the Overall input 'Working days per sprint' from the delivery start date. Forecast: the sprint's planned working days (the days of delivery, sprint by sprint) at the delivery team's and the environments' daily cost, plus any Claude API budget. Actual, up to the last actual activity (the latest completed story or day of Claude usage): the days worked in the sprint, the stories completed, the Claude API cost on its days, and the team at the days worked unless timesheets are entered. Sprints past the plan appear when work ran over. Blue cells are inputs.
Last actual activity
Sprint | Start | End | Planned days | Planned stories | Team cost (USD) | Infra cost (USD) | Claude API budget (USD) | Forecast total (USD) | Days worked | Stories done | Stories done (list) | Claude API actual (USD) | Actual team cost, timesheets (USD) | Actual total (USD) | Cost variance (USD)
1 |  |  |  | 1.1 Terraform resource groups and least-privilege Jenkins identity 1.2 AKS with Node Auto Provisioning, Istio mTLS STRICT and Kong ingress 1.3 Vault with Key Vault auto-unseal and secret-free services 1.4 Parallel microservice image builds with Kaniko on Jenkins agents 1.5 Private endpoints and private DNS for lake, SQL, Key Vault and Event Hubs | [6 empty] | 1-1-terraform-resource-groups-and 1-2-aks-with-node-auto 1-3-vault-with-key-vault 1-4-parallel-microservice-image-builds
2 |  |  |  | 1.6 Cost guardrails: Databricks cluster policy and clean terraform destroy 2.1 Entra External ID sign-in and company-scoped sessions 2.2 Row-level security for company isolation with blocked-access logging 2.3 Cash position and liquidity dashboard from the serving schema 2.4 Accounts, balances and transactions | [6 empty] | 1-5-private-endpoints-and-private 1-6-cost-guardrails-databricks-cluster 2-1-entra-external-id-sign-in 2-2-row-level-security-for-company
3 |  |  |  | 2.5 Payment creation with maker-checker approval and execution 2.6 Portal chrome: region badge, synthetic-data banner and error states 3.1 Seeded synthetic world: companies, payroll cycles, suppliers and planted anomalies 3.2 Outbox relay from the SQL ledger to Event Hubs | [6 empty] | 2-3-cash-position-and-liquidity
4 |  |  |  | 3.3 Bronze ingestion from the Event Hubs Kafka endpoint 3.4 Silver and gold Delta transforms with serving-schema write-back 3.5 Behind-the-scenes stage panel 4.1 Unity Catalog lineage from gold back to the Event Hubs source
5 |  |  |  | 4.2 Cash forecast model tracked in MLflow and registered in Unity Catalog 4.3 Isolation Forest payment anomaly detection 4.4 Batch scoring into forecasts and anomalies tables 4.5 Forecast screen and anomaly flags in the portal
6 |  |  |  | 5.1 Region-2 AKS from the same Terraform module 5.2 Front Door origins, health probes and Front Door-only ingress 5.3 SQL failover group behind a Terraform flag 5.4 Grafana requests-per-second by region 5.5 Regional failover drill and runbook
7 |  |  |  | 6.1 Security controls evidence pack for the CISO review 6.2 PDPA data-protection assessment and penetration test remediation 6.3 UAT with Group Treasury and business sign-off
8 |  |  |  | 6.4 CAB approval, production cut-over and hypercare
9
10
11
Total
Formulas:
Start = IF(OR([Planned days]="",ProjectStart=""),"",WORKDAY(ProjectStart,(1-1)*SprintDays))
End = IF([Start]="","",WORKDAY([Start],SprintDays-1))
Days worked = IF(OR([Start]="",LastActual="",[Start]>N(LastActual)),"",NETWORKDAYS([Start],MIN([End],LastActual)))

## Phase Budgets
Phase budgets: Claude API budget and actual per planning phase
In USD, at Claude API list prices. The budget each planning phase may spend (test design, governance, diagrams, course corrections ...), set once the epics and sprint plan are done; the epics and sprints carry their own budgets on their sheets. Actual: the phase's Claude cost from the ledger (Claude Usage Detail) once the close-out sheets are in. A control figure: not added to any total. Blue cells are inputs; name a phase as the token ledger does.
Phase | Claude API budget (USD) | Claude API actual (USD) | Variance (USD) | Variance % | Cited from
brainstorming | 15 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
spec | 30 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
architecture | 55 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
UX design | 45 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
governance (Jules) | 20 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
architecture docs (Da Vinci) | 25 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
epics & stories | 35 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
merges, promotions & deploys | 30 |  |  |  | assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Total

## Revenue
Revenue
Revenue the solution earns, per year after go-live, in USD, from the owner or the business case; each stream cites its source. Years past the horizon are ignored. Blue cells are inputs.
# | Stream | Basis | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Cited from | Note
Total

## Rate Card
Employee rate card
Day rates in USD. Source: owner, 2026-09-28 (blended average day rate per person); updated 2026-09-30. Blue cells are inputs; the team and support tables look roles up here.
Role | Day rate (USD) | Note
Team member (blended) | 800 | blended average across delivery roles
Delivery lead | 800 | blended rate
Solution architect | 800 | blended rate
Full-stack developer | 800 | blended rate
Mobile developer | 800 | blended rate
Cloud / DevOps engineer | 800 | blended rate
Data engineer | 800 | blended rate
QA engineer | 800 | blended rate
UX designer | 800 | blended rate
Support engineer | 800 | blended rate, run support (OPEX)

## Other Costs
Other one-off costs
Licences, tests, training and other one-off costs of the build, outside the environments and the team, in USD.
# | Item | Amount (USD) | Cited from | Note | Epic
1 | Penetration test (external CREST tester) | 18000 | assumption: pre-go-live pen test required by Sentral's Group Security; synthetic portfolio figure, owner request 2026-09-30 |  | 6
2 | PDPA data-protection impact assessment | 7500 | assumption: external privacy counsel for PDPA 2010 and cross-border transfer; synthetic portfolio figure, owner request 2026-09-30 |  | 6
Total

## Run Costs
Recurring run costs (OPEX)
Yearly costs of running the solution outside the cloud environments and the support team: support contracts, licences, subscriptions. In USD per year; the Multi-Year sheet escalates them by the yearly increase.
# | Item | Annual cost (USD) | Cited from | Note
1 | Annual penetration test | 15000 | assumption: Sentral Group Security policy, yearly retest; synthetic portfolio figure, owner request 2026-09-30
Total

## Dev
Dev environment
Azure retail list prices (pay-as-you-go) in westus3, USD, fetched 2026-09-30. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | AKS system node | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 1 | 220 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md AKS with Node Auto Provisioning | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | One regular system node; cluster stopped nights and weekends (~220 h/month), per cost-budget.md | Dev
2 | AKS spot service nodes | Virtual Machines | Standard_D4s_v5 Spot | 1 Hour | 0.035597 | 2 | 220 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md spot nodes for services during development | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5 Spot, westus3, USD per 1 Hour, meterId 6e242d37-4313-55fe-aa86-eb489f126a81, fetched 2026-09-30 | Karpenter spot nodes, stopped with the cluster | Dev
3 | Azure SQL ledger (Basic) | SQL Database | Basic 5 DTU | 1/Day | 0.161 | 1 | 30.4167 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Basic tier during development | Azure Retail Prices API, SQL Database Single Basic / B DTU, westus3, USD per 1/Day, meterId cae64797-9ecf-4906-b517-6238c80c045f, fetched 2026-09-30 |  | Dev
4 | Event Hubs namespace | Event Hubs | Standard, 1 TU | 1 Hour | 0.03 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Event Hubs Standard (1 TU, 7-day retention) | Azure Retail Prices API, Event Hubs / Standard Throughput Unit, westus3, USD per 1 Hour, meterId 62d94a65-9300-48a6-8c15-0e70fc41eb44, fetched 2026-09-30 |  | Dev
5 | Databricks jobs compute (DBU) | Azure Databricks | Premium Jobs Compute | 1 Hour | 0.3 | 1 | 40 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Databricks Premium: | Azure Retail Prices API, Azure Databricks / Premium Jobs Compute DBU, westus3, USD per 1 Hour, meterId 8ee07b23-82ae-430e-a417-a050463ff4ee, fetched 2026-09-30 | assumption: single-node D4s_v5 at 1 DBU/h, ~40 h a month of on-demand runs (cluster policy auto-stops after 10 min); synthetic portfolio figure, owner request 2026-09-30 | Dev
6 | Databricks cluster VM | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 1 | 40 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Cluster policy: single node, smallest VM, auto-stop after 10 minutes | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | same ~40 h a month as the DBUs | Dev
7 | Data lake (ADLS Gen2) | Storage | Hot LRS, hierarchical namespace | 1 GB/Month | 0.0184 | 100 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Medallion: ADLS Gen2 | Azure Retail Prices API, Azure Data Lake Storage Gen2 Hierarchical Namespace / Hot LRS Data Stored, westus3, USD per 1 GB/Month, meterId 08da9c52-d07e-566a-8952-89c0e93464b6, fetched 2026-09-30 | assumption: 100 GB of synthetic bronze/silver/gold data; synthetic portfolio figure, owner request 2026-09-30 | Dev
8 | Key Vault operations | Key Vault | Standard | 10K | 0.03 | 10 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md HashiCorp Vault for app secrets | Azure Retail Prices API, Key Vault / Operations (Standard), westus3, USD per 10K, meterId 0f824807-2376-435c-95c9-f992b67a07b0, fetched 2026-09-30 | assumption: 100K operations a month (Vault auto-unseal and root credentials); synthetic portfolio figure, owner request 2026-09-30 | Dev
9 | Private endpoints | Virtual Network | Standard Private Endpoint | 1 Hour | 0.01 | 4 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Private Endpoint, Global, USD per 1 Hour, meterId e6ab7238-e433-4fe0-a2b2-2b2564df2cdb, fetched 2026-09-30 | 4 endpoints (lake, SQL, Key Vault, Event Hubs per region) | Dev
10 | Private endpoint data processed | Virtual Network | Private Link data processed | 1 GB | 0.01 | 1 | 20 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Data Processed - Ingress, Global, USD per 1 GB, meterId 10caa28b-6479-4852-9eb7-610870cb6417, fetched 2026-09-30 | assumption: 20 GB a month through the private endpoints; synthetic portfolio figure, owner request 2026-09-30 | Dev
11 | Private DNS zones | Azure DNS | Private Zone | 1/Month | 0.5 | 4 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Azure DNS / Private Zone, Zone 1, USD per 1, meterId 0b608a26-f611-4232-8192-ce81b6b57194, fetched 2026-09-30 | one zone per private-endpoint service | Dev
12 | NAT gateway (Databricks egress) | NAT Gateway | Standard | 1 Hour | 0.045 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Gateway, Global, USD per 1 Hour, meterId ae30040a-67f5-485b-b0f4-a6ef50504d9c, fetched 2026-09-30 |  | Dev
13 | NAT gateway data processed | NAT Gateway | Standard data processed | 1 GB | 0.045 | 1 | 20 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Data Processed, Global, USD per 1 GB, meterId d32b6352-b66b-4c4c-8f21-60e94058e04d, fetched 2026-09-30 | assumption: 20 GB of Databricks egress a month; synthetic portfolio figure, owner request 2026-09-30 | Dev
14 | Kong ingress load balancer | Load Balancer | Standard | 1 Hour | 0.025 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, Load Balancer / Standard Included LB Rules and Outbound Rules, Global, USD per 1 Hour, meterId 27827eb0-7f60-4928-940b-f5fe15e7a4cb, fetched 2026-09-30 |  | Dev
15 | Ingress public IPs | Virtual Network | Standard IPv4 static | 1 Hour | 0.005 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, IP Addresses / Standard IPv4 Static Public IP, westus3, USD per 1 Hour, meterId 9c150bf9-2bad-430e-a53c-c213804f49ef, fetched 2026-09-30 |  | Dev
Dev
Dev
Dev
Total

## Test
Test environment
Azure retail list prices (pay-as-you-go) in westus3, USD, fetched 2026-09-30. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | AKS nodes | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 2 | 260 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md AKS with Node Auto Provisioning | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | assumption: 2 regular nodes, weekdays 12 h a day (~260 h/month); stopped otherwise; synthetic portfolio figure, owner request 2026-09-30 | Test
2 | Azure SQL ledger (S1) | SQL Database | Standard S1 20 DTU | 1/Day | 0.9677 | 1 | 30.4167 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Operational ledger, including payment approval state and an outbox table | Azure Retail Prices API, SQL Database Single Standard / S1 DTUs, westus3, USD per 1/Day, meterId 54c6bbf3-322b-406d-8411-101bc4b9443a, fetched 2026-09-30 | assumption: S1 for integration and regression runs; synthetic portfolio figure, owner request 2026-09-30 | Test
3 | Event Hubs namespace | Event Hubs | Standard, 1 TU | 1 Hour | 0.03 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Event Hubs Standard (1 TU, 7-day retention) | Azure Retail Prices API, Event Hubs / Standard Throughput Unit, westus3, USD per 1 Hour, meterId 62d94a65-9300-48a6-8c15-0e70fc41eb44, fetched 2026-09-30 |  | Test
4 | Databricks jobs compute (DBU) | Azure Databricks | Premium Jobs Compute | 1 Hour | 0.3 | 1 | 60 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Databricks Premium: | Azure Retail Prices API, Azure Databricks / Premium Jobs Compute DBU, westus3, USD per 1 Hour, meterId 8ee07b23-82ae-430e-a417-a050463ff4ee, fetched 2026-09-30 | assumption: single node at 1 DBU/h, ~60 h a month of test runs; synthetic portfolio figure, owner request 2026-09-30 | Test
5 | Databricks cluster VM | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 1 | 60 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Databricks Premium: | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | same ~60 h a month as the DBUs | Test
6 | Data lake (ADLS Gen2) | Storage | Hot LRS, hierarchical namespace | 1 GB/Month | 0.0184 | 200 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Medallion: ADLS Gen2 | Azure Retail Prices API, Azure Data Lake Storage Gen2 Hierarchical Namespace / Hot LRS Data Stored, westus3, USD per 1 GB/Month, meterId 08da9c52-d07e-566a-8952-89c0e93464b6, fetched 2026-09-30 | assumption: 200 GB of synthetic test data; synthetic portfolio figure, owner request 2026-09-30 | Test
7 | Key Vault operations | Key Vault | Standard | 10K | 0.03 | 20 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md HashiCorp Vault for app secrets | Azure Retail Prices API, Key Vault / Operations (Standard), westus3, USD per 10K, meterId 0f824807-2376-435c-95c9-f992b67a07b0, fetched 2026-09-30 | assumption: 200K operations a month; synthetic portfolio figure, owner request 2026-09-30 | Test
8 | Private endpoints | Virtual Network | Standard Private Endpoint | 1 Hour | 0.01 | 4 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Private Endpoint, Global, USD per 1 Hour, meterId e6ab7238-e433-4fe0-a2b2-2b2564df2cdb, fetched 2026-09-30 | 4 endpoints (lake, SQL, Key Vault, Event Hubs per region) | Test
9 | Private endpoint data processed | Virtual Network | Private Link data processed | 1 GB | 0.01 | 1 | 40 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Data Processed - Ingress, Global, USD per 1 GB, meterId 10caa28b-6479-4852-9eb7-610870cb6417, fetched 2026-09-30 | assumption: 40 GB a month through the private endpoints; synthetic portfolio figure, owner request 2026-09-30 | Test
10 | Private DNS zones | Azure DNS | Private Zone | 1/Month | 0.5 | 4 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Azure DNS / Private Zone, Zone 1, USD per 1, meterId 0b608a26-f611-4232-8192-ce81b6b57194, fetched 2026-09-30 | one zone per private-endpoint service | Test
11 | NAT gateway (Databricks egress) | NAT Gateway | Standard | 1 Hour | 0.045 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Gateway, Global, USD per 1 Hour, meterId ae30040a-67f5-485b-b0f4-a6ef50504d9c, fetched 2026-09-30 |  | Test
12 | NAT gateway data processed | NAT Gateway | Standard data processed | 1 GB | 0.045 | 1 | 30 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Data Processed, Global, USD per 1 GB, meterId d32b6352-b66b-4c4c-8f21-60e94058e04d, fetched 2026-09-30 | assumption: 30 GB of Databricks egress a month; synthetic portfolio figure, owner request 2026-09-30 | Test
13 | Kong ingress load balancer | Load Balancer | Standard | 1 Hour | 0.025 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, Load Balancer / Standard Included LB Rules and Outbound Rules, Global, USD per 1 Hour, meterId 27827eb0-7f60-4928-940b-f5fe15e7a4cb, fetched 2026-09-30 |  | Test
14 | Ingress public IPs | Virtual Network | Standard IPv4 static | 1 Hour | 0.005 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, IP Addresses / Standard IPv4 Static Public IP, westus3, USD per 1 Hour, meterId 9c150bf9-2bad-430e-a53c-c213804f49ef, fetched 2026-09-30 |  | Test
Test
Test
Test
Total

## UAT
UAT environment
Azure retail list prices (pay-as-you-go) in westus3, USD, fetched 2026-09-30. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | AKS uptime SLA | Azure Kubernetes Service | Standard tier | 1 Hour | 0.1 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md AKS with Node Auto Provisioning | Azure Retail Prices API, Azure Kubernetes Service / Standard Uptime SLA, westus3, USD per 1 Hour, meterId 251a08e1-40d6-48e6-8368-4c3e5ee3bbff, fetched 2026-09-30 | assumption: Standard tier so UAT matches Prod's control plane; synthetic portfolio figure, owner request 2026-09-30 | UAT
2 | AKS nodes | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 3 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md AKS with Node Auto Provisioning | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | assumption: prod-like but smaller: 3 always-on nodes, one region; synthetic portfolio figure, owner request 2026-09-30 | UAT
3 | Azure SQL ledger (GP 2 vCore) | SQL Database | General Purpose Gen5 2 vCore | 1 Hour | 0.30443 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Operational ledger, including payment approval state and an outbox table | Azure Retail Prices API, SQL Database Single/Elastic Pool General Purpose - Compute Gen5 / vCore (2 vCore), westus3, USD per 1 Hour, meterId ed73d792-d844-5a0d-a685-a23c087bd0bc, fetched 2026-09-30 | assumption: General Purpose 2 vCore, prod tier at half the size; synthetic portfolio figure, owner request 2026-09-30 | UAT
4 | Azure SQL storage | SQL Database | General Purpose data stored | 1 GB/Month | 0.115 | 100 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Operational ledger, including payment approval state and an outbox table | Azure Retail Prices API, SQL Database Single/Elastic Pool General Purpose - Storage / General Purpose Data Stored, westus3, USD per 1 GB/Month, meterId d59e97de-70e6-5505-8346-fdcbca6938b2, fetched 2026-09-30 | assumption: 100 GB; synthetic portfolio figure, owner request 2026-09-30 | UAT
5 | Event Hubs namespace | Event Hubs | Standard, 1 TU | 1 Hour | 0.03 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Event Hubs Standard (1 TU, 7-day retention) | Azure Retail Prices API, Event Hubs / Standard Throughput Unit, westus3, USD per 1 Hour, meterId 62d94a65-9300-48a6-8c15-0e70fc41eb44, fetched 2026-09-30 |  | UAT
6 | Databricks jobs compute (DBU) | Azure Databricks | Premium Jobs Compute | 1 Hour | 0.3 | 1 | 120 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Databricks Premium: | Azure Retail Prices API, Azure Databricks / Premium Jobs Compute DBU, westus3, USD per 1 Hour, meterId 8ee07b23-82ae-430e-a417-a050463ff4ee, fetched 2026-09-30 | assumption: single node at 1 DBU/h, ~120 h a month of UAT batches; synthetic portfolio figure, owner request 2026-09-30 | UAT
7 | Databricks cluster VM | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 1 | 120 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Databricks Premium: | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | same ~120 h a month as the DBUs | UAT
8 | Data lake (ADLS Gen2) | Storage | Hot ZRS, hierarchical namespace | 1 GB/Month | 0.023 | 500 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Medallion: ADLS Gen2 | Azure Retail Prices API, Azure Data Lake Storage Gen2 Hierarchical Namespace / Hot ZRS Data Stored, westus3, USD per 1 GB/Month, meterId 65f37adb-2a94-5d80-80e8-8a0bcd54d1aa, fetched 2026-09-30 | assumption: 500 GB, zone-redundant like Prod; synthetic portfolio figure, owner request 2026-09-30 | UAT
9 | Key Vault operations | Key Vault | Standard | 10K | 0.03 | 60 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md HashiCorp Vault for app secrets | Azure Retail Prices API, Key Vault / Operations (Standard), westus3, USD per 10K, meterId 0f824807-2376-435c-95c9-f992b67a07b0, fetched 2026-09-30 | assumption: 600K operations a month; synthetic portfolio figure, owner request 2026-09-30 | UAT
10 | Front Door | Azure Front Door Service | Standard base fee | 1/Month | 35 | 1 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Front Door Standard | Azure Retail Prices API, Azure Front Door / Standard Base Fees, Zone 1, USD per 1/Month, meterId 7e3eab72-0b95-5524-984a-d1697f73feee, fetched 2026-09-30 | Standard, never Premium (SPEC constraints) | UAT
11 | Log Analytics ingestion | Log Analytics | Analytics Logs | 1 GB | 2.3 | 15 | 1 |  |  |  | assumption: AKS and SQL diagnostics, ~15 GB a month billed; synthetic portfolio figure, owner request 2026-09-30 | Azure Retail Prices API, Log Analytics / Analytics Logs Data Ingestion (above the 5 GB free tier), westus3, USD per 1 GB, meterId ffbd06c0-e72e-42b6-b612-f03144b476df, fetched 2026-09-30 | Prometheus and Grafana run in the cluster | UAT
12 | Private endpoints | Virtual Network | Standard Private Endpoint | 1 Hour | 0.01 | 4 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Private Endpoint, Global, USD per 1 Hour, meterId e6ab7238-e433-4fe0-a2b2-2b2564df2cdb, fetched 2026-09-30 | 4 endpoints (lake, SQL, Key Vault, Event Hubs per region) | UAT
13 | Private endpoint data processed | Virtual Network | Private Link data processed | 1 GB | 0.01 | 1 | 150 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Data Processed - Ingress, Global, USD per 1 GB, meterId 10caa28b-6479-4852-9eb7-610870cb6417, fetched 2026-09-30 | assumption: 150 GB a month through the private endpoints; synthetic portfolio figure, owner request 2026-09-30 | UAT
14 | Private DNS zones | Azure DNS | Private Zone | 1/Month | 0.5 | 4 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Azure DNS / Private Zone, Zone 1, USD per 1, meterId 0b608a26-f611-4232-8192-ce81b6b57194, fetched 2026-09-30 | one zone per private-endpoint service | UAT
15 | NAT gateway (Databricks egress) | NAT Gateway | Standard | 1 Hour | 0.045 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Gateway, Global, USD per 1 Hour, meterId ae30040a-67f5-485b-b0f4-a6ef50504d9c, fetched 2026-09-30 |  | UAT
16 | NAT gateway data processed | NAT Gateway | Standard data processed | 1 GB | 0.045 | 1 | 60 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Data Processed, Global, USD per 1 GB, meterId d32b6352-b66b-4c4c-8f21-60e94058e04d, fetched 2026-09-30 | assumption: 60 GB of Databricks egress a month; synthetic portfolio figure, owner request 2026-09-30 | UAT
17 | Kong ingress load balancer | Load Balancer | Standard | 1 Hour | 0.025 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, Load Balancer / Standard Included LB Rules and Outbound Rules, Global, USD per 1 Hour, meterId 27827eb0-7f60-4928-940b-f5fe15e7a4cb, fetched 2026-09-30 |  | UAT
18 | Ingress public IPs | Virtual Network | Standard IPv4 static | 1 Hour | 0.005 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, IP Addresses / Standard IPv4 Static Public IP, westus3, USD per 1 Hour, meterId 9c150bf9-2bad-430e-a53c-c213804f49ef, fetched 2026-09-30 |  | UAT
UAT
UAT
UAT
Total

## Prod
Prod environment
Azure retail list prices (pay-as-you-go) in westus3, USD, fetched 2026-09-30. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | AKS uptime SLA, both regions | Azure Kubernetes Service | Standard tier | 1 Hour | 0.1 | 2 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md AKS with Node Auto Provisioning | Azure Retail Prices API, Azure Kubernetes Service / Standard Uptime SLA, westus3, USD per 1 Hour, meterId 251a08e1-40d6-48e6-8368-4c3e5ee3bbff, fetched 2026-09-30 | West US 3 and North Central US clusters; both priced at the same list meter | Prod
2 | AKS system nodes, West US 3 | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 3 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md AKS with Node Auto Provisioning | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | assumption: 3 system nodes across availability zones; synthetic portfolio figure, owner request 2026-09-30 | Prod
3 | AKS service nodes, West US 3 | Virtual Machines | Standard_D8s_v5 | 1 Hour | 0.384 | 3 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md AKS with Node Auto Provisioning | Azure Retail Prices API, Virtual Machines Dsv5 Series / D8s v5, westus3, USD per 1 Hour, meterId 78f46250-07b1-5b70-be7a-54b964dcf1c2, fetched 2026-09-30 | assumption: 3 service nodes for the microservices, Kong, Vault and monitoring; synthetic portfolio figure, owner request 2026-09-30 | Prod
4 | AKS nodes, North Central US | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 3 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md the same Terraform module applied to North Central US | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, northcentralus, USD per 1 Hour, meterId f85b750a-42a9-5bd6-aea5-dea01bb8fcfb, fetched 2026-09-30 | active second region behind Front Door (CAP-12) | Prod
5 | Azure SQL ledger primary (GP 4 vCore) | SQL Database | General Purpose Gen5 4 vCore | 1 Hour | 0.60887 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Operational ledger, including payment approval state and an outbox table | Azure Retail Prices API, SQL Database Single/Elastic Pool General Purpose - Compute Gen5 / vCore (4 vCore), westus3, USD per 1 Hour, meterId ed73d792-d844-5a0d-a685-a23c087bd0bc, fetched 2026-09-30 | assumption: General Purpose 4 vCore for ~6,500 registered users; synthetic portfolio figure, owner request 2026-09-30 | Prod
6 | Azure SQL geo-secondary, North Central US | SQL Database | General Purpose Gen5 4 vCore | 1 Hour | 0.60887 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md `enable_sql_failover` flag | Azure Retail Prices API, SQL Database Single/Elastic Pool General Purpose - Compute Gen5 / vCore (4 vCore), northcentralus, USD per 1 Hour, meterId d6a98653-89d1-4981-a1bd-f44dcfd14fa2, fetched 2026-09-30 | failover group secondary, always on in Prod (CAP-13) | Prod
7 | Azure SQL storage, both regions | SQL Database | General Purpose data stored | 1 GB/Month | 0.115 | 500 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Operational ledger, including payment approval state and an outbox table | Azure Retail Prices API, SQL Database Single/Elastic Pool General Purpose - Storage / General Purpose Data Stored, westus3, USD per 1 GB/Month, meterId d59e97de-70e6-5505-8346-fdcbca6938b2, fetched 2026-09-30 | assumption: 250 GB per region; synthetic portfolio figure, owner request 2026-09-30 | Prod
8 | Event Hubs throughput units | Event Hubs | Standard | 1 Hour | 0.03 | 2 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Event Hubs Standard (1 TU, 7-day retention) | Azure Retail Prices API, Event Hubs / Standard Throughput Unit, westus3, USD per 1 Hour, meterId 62d94a65-9300-48a6-8c15-0e70fc41eb44, fetched 2026-09-30 | assumption: 2 TUs for production payment and ledger events; synthetic portfolio figure, owner request 2026-09-30 | Prod
9 | Event Hubs ingress events | Event Hubs | Standard ingress | 1M | 0.028 | 30 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Event Hubs Standard (1 TU, 7-day retention) | Azure Retail Prices API, Event Hubs / Standard Ingress Events, westus3, USD per 1M, meterId d0a685ee-f093-4c5c-ba76-3ec342a75de7, fetched 2026-09-30 | assumption: 30 million events a month; synthetic portfolio figure, owner request 2026-09-30 | Prod
10 | Databricks jobs compute (DBU) | Azure Databricks | Premium Jobs Compute | 1 Hour | 0.3 | 2 | 365 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Databricks Premium: | Azure Retail Prices API, Azure Databricks / Premium Jobs Compute DBU, westus3, USD per 1 Hour, meterId 8ee07b23-82ae-430e-a417-a050463ff4ee, fetched 2026-09-30 | assumption: 2-node jobs cluster at 1 DBU/h per node, micro-batches ~12 h a day (365 h/month), plus nightly forecast and anomaly scoring; synthetic portfolio figure, owner request 2026-09-30 | Prod
11 | Databricks cluster VMs | Virtual Machines | Standard_D4s_v5 | 1 Hour | 0.192 | 2 | 365 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Databricks Premium: | Azure Retail Prices API, Virtual Machines Dsv5 Series / D4s v5, westus3, USD per 1 Hour, meterId a7d0753e-6fcd-5b61-8b6e-4727c10691a1, fetched 2026-09-30 | same 365 h a month as the DBUs | Prod
12 | Data lake (ADLS Gen2) | Storage | Hot GRS, hierarchical namespace | 1 GB/Month | 0.0368 | 2000 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Medallion: ADLS Gen2 | Azure Retail Prices API, Azure Data Lake Storage Gen2 Hierarchical Namespace / Hot GRS Data Stored, westus3, USD per 1 GB/Month, meterId 8b94aff2-e31b-5a24-8828-34951d2ced75, fetched 2026-09-30 | assumption: 2 TB medallion, geo-redundant (GRS pair); synthetic portfolio figure, owner request 2026-09-30 | Prod
13 | Key Vault operations | Key Vault | Standard | 10K | 0.03 | 300 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md HashiCorp Vault for app secrets | Azure Retail Prices API, Key Vault / Operations (Standard), westus3, USD per 10K, meterId 0f824807-2376-435c-95c9-f992b67a07b0, fetched 2026-09-30 | assumption: 3M operations a month; synthetic portfolio figure, owner request 2026-09-30 | Prod
14 | Front Door | Azure Front Door Service | Standard base fee | 1/Month | 35 | 1 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Front Door Standard | Azure Retail Prices API, Azure Front Door / Standard Base Fees, Zone 1, USD per 1/Month, meterId 7e3eab72-0b95-5524-984a-d1697f73feee, fetched 2026-09-30 | origin per region with health probes | Prod
15 | Front Door data transfer out | Azure Front Door Service | Standard data transfer out | 1 GB | 0.0825 | 1 | 400 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Front Door Standard | Azure Retail Prices API, Azure Front Door / Standard Data Transfer Out, Zone 1, USD per 1 GB, meterId 79b4d346-f8f7-55fe-8375-5943ea4e697c, fetched 2026-09-30 | assumption: 400 GB a month to treasury users; synthetic portfolio figure, owner request 2026-09-30 | Prod
16 | Log Analytics ingestion | Log Analytics | Analytics Logs | 1 GB | 2.3 | 60 | 1 |  |  |  | assumption: AKS, SQL, Front Door and audit diagnostics, ~60 GB a month billed; synthetic portfolio figure, owner request 2026-09-30 | Azure Retail Prices API, Log Analytics / Analytics Logs Data Ingestion (above the 5 GB free tier), westus3, USD per 1 GB, meterId ffbd06c0-e72e-42b6-b612-f03144b476df, fetched 2026-09-30 |  | Prod
17 | Private endpoints | Virtual Network | Standard Private Endpoint | 1 Hour | 0.01 | 8 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Private Endpoint, Global, USD per 1 Hour, meterId e6ab7238-e433-4fe0-a2b2-2b2564df2cdb, fetched 2026-09-30 | 8 endpoints (lake, SQL, Key Vault, Event Hubs per region) | Prod
18 | Private endpoint data processed | Virtual Network | Private Link data processed | 1 GB | 0.01 | 1 | 800 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Virtual Network Private Link / Standard Data Processed - Ingress, Global, USD per 1 GB, meterId 10caa28b-6479-4852-9eb7-610870cb6417, fetched 2026-09-30 | assumption: 800 GB a month through the private endpoints; synthetic portfolio figure, owner request 2026-09-30 | Prod
19 | Private DNS zones | Azure DNS | Private Zone | 1/Month | 0.5 | 4 | 1 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Private endpoints: ADLS, SQL, Key Vault and Event Hubs | Azure Retail Prices API, Azure DNS / Private Zone, Zone 1, USD per 1, meterId 0b608a26-f611-4232-8192-ce81b6b57194, fetched 2026-09-30 | one zone per private-endpoint service | Prod
20 | NAT gateway (Databricks egress) | NAT Gateway | Standard | 1 Hour | 0.045 | 1 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Gateway, Global, USD per 1 Hour, meterId ae30040a-67f5-485b-b0f4-a6ef50504d9c, fetched 2026-09-30 |  | Prod
21 | NAT gateway data processed | NAT Gateway | Standard data processed | 1 GB | 0.045 | 1 | 300 |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md VNet-injected with a NAT gateway | Azure Retail Prices API, NAT Gateway / Standard Data Processed, Global, USD per 1 GB, meterId d32b6352-b66b-4c4c-8f21-60e94058e04d, fetched 2026-09-30 | assumption: 300 GB of Databricks egress a month; synthetic portfolio figure, owner request 2026-09-30 | Prod
22 | Kong ingress load balancer | Load Balancer | Standard | 1 Hour | 0.025 | 2 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, Load Balancer / Standard Included LB Rules and Outbound Rules, Global, USD per 1 Hour, meterId 27827eb0-7f60-4928-940b-f5fe15e7a4cb, fetched 2026-09-30 |  | Prod
23 | Ingress public IPs | Virtual Network | Standard IPv4 static | 1 Hour | 0.005 | 3 |  |  |  |  | _bmad-output/specs/spec-corporate-portal-poc/stack.md Kong OSS as the API gateway (ingress) | Azure Retail Prices API, IP Addresses / Standard IPv4 Static Public IP, westus3, USD per 1 Hour, meterId 9c150bf9-2bad-430e-a53c-c213804f49ef, fetched 2026-09-30 |  | Prod
Prod
Prod
Prod
Total

## Claude Prices
Claude API list prices
USD per million tokens, from https://platform.claude.com/docs/en/about-claude/pricing, read 2026-09-28. Blue cells are inputs.
Pricing model | Name | Input | Cache write 5m | Cache write 1h | Cache read | Output
claude-fable-5 | Claude Fable 5 | 10 | 12.5 | 20 | 1 | 50
claude-fable-5-1 | Claude Fable 5.1 | 10 | 12.5 | 20 | 0.25 | 50
claude-haiku-3-5 | Claude Haiku 3.5 | 0.8 | 1 | 1.6 | 0.08 | 4
claude-haiku-4-5 | Claude Haiku 4.5 | 1 | 1.25 | 2 | 0.1 | 5
claude-mythos-5 | Claude Mythos 5 | 10 | 12.5 | 20 | 1 | 50
claude-mythos-5-1 | Claude Mythos 5.1 | 10 | 12.5 | 20 | 0.25 | 50
claude-opus-4 | Claude Opus 4 | 15 | 18.75 | 30 | 1.5 | 75
claude-opus-4-1 | Claude Opus 4.1 | 15 | 18.75 | 30 | 1.5 | 75
claude-opus-4-5 | Claude Opus 4.5 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-4-6 | Claude Opus 4.6 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-4-7 | Claude Opus 4.7 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-4-8 | Claude Opus 4.8 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-5 | Claude Opus 5 | 5 | 6.25 | 10 | 0.5 | 25
claude-opus-5-5 | Claude Opus 5.5 | 4 | 5 | 8 | 0.2 | 20
claude-sonnet-4 | Claude Sonnet 4 | 3 | 3.75 | 6 | 0.3 | 15
claude-sonnet-4-5 | Claude Sonnet 4.5 | 3 | 3.75 | 6 | 0.3 | 15
claude-sonnet-4-6 | Claude Sonnet 4.6 | 3 | 3.75 | 6 | 0.3 | 15
claude-sonnet-5 | Claude Sonnet 5 | 2 | 2.5 | 4 | 0.2 | 10

## Claude Usage
Claude API usage
API calls and tokens counted from this project's Claude Code logs, costed at Claude API list prices. On a Pro, Max, Team or Enterprise subscription the bill is per seat: this is the API-equivalent cost.
Model | Calls | Input tokens | Cache write 5m tokens | Cache write 1h tokens | Cache read tokens | Output tokens | Cost (USD) | Cost (USD)
claude-opus-5-5
Total

## Claude Usage Detail
Claude API calls by work item and model
From the token ledger (claude_usage.csv). Cost = tokens x the Claude Prices sheet; models with no price cost 0.
Kind | Work item | Story no | Title | Model | Pricing model | First call | Last call | Calls | Input tokens | Cache write 5m tokens | Cache write 1h tokens | Cache read tokens | Output tokens | Cost (USD) | Cost (USD) | Person
planning | brainstorming |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-07-27 02:09 | 2026-07-28 07:05 | 249 | 1336 | 787578 | 95552 | 36378953 | 218823
planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-07-29 01:24 | 2026-08-04 08:02 | 505 | 3349 | 1631310 | 199573 | 76363270 | 428416
planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-08-05 02:04 | 2026-08-14 10:04 | 918 | 5391 | 2910859 | 327068 | 136162160 | 787929
planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-08-10 01:15 | 2026-08-19 07:37 | 710 | 4186 | 2374598 | 265445 | 109983933 | 665082
planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-08-17 01:14 | 2026-08-21 08:18 | 373 | 1921 | 1096280 | 117012 | 52904915 | 313479
planning | architecture docs (Da Vinci) |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-08-18 03:08 | 2026-08-24 08:07 | 369 | 2304 | 1246510 | 137111 | 56652932 | 337590
planning | epics & stories |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-08-24 03:12 | 2026-08-27 07:36 | 589 | 3648 | 1836552 | 215131 | 87107660 | 509632
ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 2026-09-01 01:32 | 2026-09-30 10:49 | 232 | 1372 | 749462 | 86220 | 34632999 | 200750
story | PORTAL-101 | 1.1 | Terraform resource groups and least-privilege Jenkins identity | claude-opus-5-5 | claude-opus-5-5 | 2026-08-31 03:59 | 2026-09-02 09:16 | 166 | 1018 | 536117 | 57656 | 24669393 | 150718
story | PORTAL-102 | 1.2 | AKS with Node Auto Provisioning, Istio mTLS STRICT and Kong ingress | claude-opus-5-5 | claude-opus-5-5 | 2026-09-02 03:49 | 2026-09-07 09:34 | 239 | 1468 | 776411 | 83287 | 35269220 | 210812
story | PORTAL-103 | 1.3 | Vault with Key Vault auto-unseal and secret-free services | claude-opus-5-5 | claude-opus-5-5 | 2026-09-07 02:46 | 2026-09-09 07:08 | 167 | 955 | 539529 | 61593 | 24192178 | 144011
story | PORTAL-104 | 1.4 | Parallel microservice image builds with Kaniko on Jenkins agents | claude-opus-5-5 | claude-opus-5-5 | 2026-09-09 01:48 | 2026-09-11 10:26 | 139 | 707 | 410579 | 48939 | 19516467 | 113978
story | PORTAL-105 | 1.5 | Private endpoints and private DNS for lake, SQL, Key Vault and Event Hubs | claude-opus-5-5 | claude-opus-5-5 | 2026-09-11 03:05 | 2026-09-15 09:22 | 140 | 807 | 440612 | 50735 | 20726280 | 125262
story | PORTAL-106 | 1.6 | Cost guardrails: Databricks cluster policy and clean terraform destroy | claude-opus-5-5 | claude-opus-5-5 | 2026-09-15 03:32 | 2026-09-16 10:05 | 82 | 482 | 228197 | 25853 | 11039650 | 63317
story | PORTAL-107 | 2.1 | Entra External ID sign-in and company-scoped sessions | claude-opus-5-5 | claude-opus-5-5 | 2026-09-17 02:31 | 2026-09-21 07:04 | 190 | 1278 | 583772 | 70755 | 28911877 | 169841
story | PORTAL-108 | 2.2 | Row-level security for company isolation with blocked-access logging | claude-opus-5-5 | claude-opus-5-5 | 2026-09-21 02:42 | 2026-09-24 10:19 | 178 | 1089 | 528592 | 60471 | 24548767 | 157378
story | PORTAL-109 | 2.3 | Cash position and liquidity dashboard from the serving schema | claude-opus-5-5 | claude-opus-5-5 | 2026-09-24 03:22 | 2026-09-28 10:22 | 148 | 918 | 463868 | 49052 | 22147665 | 136099
story | PORTAL-110 | 2.4 | Accounts, balances and transactions | claude-opus-5-5 | claude-opus-5-5 | 2026-09-28 01:31 | 2026-09-30 09:09 | 90 | 499 | 290789 | 34375 | 14033359 | 79685
story | PORTAL-111 | 2.5 | Payment creation with maker-checker approval and execution | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 02:26 | 2026-08-25 10:05 | 20 | 90 | 57544 | 6553 | 2710803 | 14873
story | PORTAL-112 | 2.6 | Portal chrome: region badge, synthetic-data banner and error states | claude-opus-5-5 | claude-opus-5-5 | 2026-08-27 02:35 | 2026-08-27 08:52 | 16 | 79 | 51347 | 4158 | 2238077 | 14180
story | PORTAL-113 | 3.1 | Seeded synthetic world: companies, payroll cycles, suppliers and planted anomalies | claude-opus-5-5 | claude-opus-5-5 | 2026-08-27 03:18 | 2026-08-27 09:44 | 19 | 109 | 58655 | 5445 | 2606398 | 16111
story | PORTAL-114 | 3.2 | Outbox relay from the SQL ledger to Event Hubs | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 01:09 | 2026-08-25 08:15 | 10 | 72 | 31119 | 3700 | 1374125 | 8714
story | PORTAL-115 | 3.3 | Bronze ingestion from the Event Hubs Kafka endpoint | claude-opus-5-5 | claude-opus-5-5 | 2026-08-26 01:32 | 2026-08-26 08:16 | 16 | 106 | 46803 | 5534 | 2271940 | 15080
story | PORTAL-116 | 3.4 | Silver and gold Delta transforms with serving-schema write-back | claude-opus-5-5 | claude-opus-5-5 | 2026-08-26 01:27 | 2026-08-26 09:09 | 13 | 109 | 48679 | 5933 | 2293063 | 10145
story | PORTAL-117 | 3.5 | Behind-the-scenes stage panel | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 03:40 | 2026-08-25 07:30 | 16 | 118 | 47657 | 5900 | 2104710 | 10964
story | PORTAL-118 | 4.1 | Unity Catalog lineage from gold back to the Event Hubs source | claude-opus-5-5 | claude-opus-5-5 | 2026-08-27 03:52 | 2026-08-27 10:25 | 11 | 86 | 41416 | 4593 | 1938969 | 10805
story | PORTAL-119 | 4.2 | Cash forecast model tracked in MLflow and registered in Unity Catalog | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 02:40 | 2026-08-25 08:04 | 9 | 62 | 30854 | 3083 | 1403160 | 8503
story | PORTAL-120 | 4.3 | Isolation Forest payment anomaly detection | claude-opus-5-5 | claude-opus-5-5 | 2026-08-26 01:07 | 2026-08-26 07:06 | 19 | 94 | 57618 | 6622 | 2712777 | 14386
story | PORTAL-121 | 4.4 | Batch scoring into forecasts and anomalies tables | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 01:34 | 2026-08-25 09:39 | 18 | 69 | 48045 | 6264 | 2478204 | 17017
story | PORTAL-122 | 4.5 | Forecast screen and anomaly flags in the portal | claude-opus-5-5 | claude-opus-5-5 | 2026-08-27 01:39 | 2026-08-27 09:23 | 11 | 62 | 34832 | 3620 | 1689013 | 10153
story | PORTAL-123 | 5.1 | Region-2 AKS from the same Terraform module | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 02:07 | 2026-08-25 10:30 | 14 | 110 | 47293 | 6727 | 2257245 | 16564
story | PORTAL-124 | 5.2 | Front Door origins, health probes and Front Door-only ingress | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 02:05 | 2026-08-25 09:47 | 13 | 51 | 36120 | 4785 | 1590908 | 11049
story | PORTAL-125 | 5.3 | SQL failover group behind a Terraform flag | claude-opus-5-5 | claude-opus-5-5 | 2026-08-27 03:11 | 2026-08-27 08:33 | 15 | 79 | 51280 | 5066 | 2473649 | 12558
story | PORTAL-126 | 5.4 | Grafana requests-per-second by region | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 03:35 | 2026-08-25 09:42 | 13 | 75 | 48527 | 5417 | 2117224 | 12626
story | PORTAL-127 | 5.5 | Regional failover drill and runbook | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 03:54 | 2026-08-25 09:58 | 14 | 134 | 48954 | 5608 | 2442046 | 14448
story | PORTAL-128 | 6.1 | Security controls evidence pack for the CISO review | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 01:35 | 2026-08-25 09:40 | 15 | 117 | 54291 | 6229 | 2641089 | 13996
story | PORTAL-129 | 6.2 | PDPA data-protection assessment and penetration test remediation | claude-opus-5-5 | claude-opus-5-5 | 2026-08-26 01:51 | 2026-08-26 10:48 | 16 | 48 | 46669 | 4208 | 2028847 | 13387
story | PORTAL-130 | 6.3 | UAT with Group Treasury and business sign-off | claude-opus-5-5 | claude-opus-5-5 | 2026-08-26 01:34 | 2026-08-26 07:02 | 14 | 87 | 45760 | 5179 | 2082456 | 8342
story | PORTAL-131 | 6.4 | CAB approval, production cut-over and hypercare | claude-opus-5-5 | claude-opus-5-5 | 2026-08-25 02:16 | 2026-08-25 09:29 | 15 | 95 | 43160 | 4790 | 2214174 | 16918

## Claude Usage Daily
Claude API usage by day
From the token ledger (claude_usage_daily.csv, refreshed after every turn). Cost = tokens x the Claude Prices sheet; models with no price cost 0.
Day | Kind | Work item | Story no | Title | Model | Pricing model | Calls | Input tokens | Cache write 5m tokens | Cache write 1h tokens | Cache read tokens | Output tokens | Cost (USD) | Cost (USD) | Person
2026-07-27 | planning | brainstorming |  |  | claude-opus-5-5 | claude-opus-5-5 | 99 | 771 | 359180 | 41815 | 15766876 | 93187
2026-07-28 | planning | brainstorming |  |  | claude-opus-5-5 | claude-opus-5-5 | 150 | 565 | 428398 | 53737 | 20612077 | 125636
2026-07-29 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 108 | 510 | 353290 | 43525 | 15311490 | 92576
2026-07-30 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 76 | 522 | 259983 | 28964 | 11561605 | 59776
2026-07-31 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 95 | 695 | 313874 | 34331 | 15562561 | 84339
2026-08-03 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 106 | 696 | 351426 | 41815 | 15867028 | 94194
2026-08-04 | planning | spec |  |  | claude-opus-5-5 | claude-opus-5-5 | 120 | 926 | 352737 | 50938 | 18060586 | 97531
2026-08-05 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 103 | 675 | 305086 | 34837 | 13942212 | 88296
2026-08-06 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 81 | 483 | 265660 | 27709 | 12282734 | 77030
2026-08-07 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 69 | 466 | 282036 | 30613 | 12564245 | 64279
2026-08-10 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 132 | 781 | 388193 | 44724 | 18611848 | 102347
2026-08-10 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 100 | 753 | 329945 | 34242 | 14554576 | 85704
2026-08-11 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 148 | 763 | 465725 | 54305 | 21437905 | 131667
2026-08-11 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 94 | 589 | 327222 | 37832 | 15081315 | 101513
2026-08-12 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 82 | 522 | 239706 | 25588 | 11946283 | 65724
2026-08-12 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 100 | 575 | 371283 | 39616 | 16730844 | 97800
2026-08-13 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 132 | 722 | 443926 | 46639 | 20244016 | 109109
2026-08-13 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 76 | 464 | 255766 | 27771 | 12252024 | 66866
2026-08-14 | planning | architecture |  |  | claude-opus-5-5 | claude-opus-5-5 | 171 | 979 | 520527 | 62653 | 25132917 | 149477
2026-08-14 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 61 | 404 | 196576 | 21882 | 9281760 | 57623
2026-08-17 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 94 | 559 | 327532 | 34843 | 15582577 | 93915
2026-08-17 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 46 | 251 | 157598 | 18000 | 7109442 | 44660
2026-08-18 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 70 | 372 | 235608 | 28551 | 11137035 | 66616
2026-08-18 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 46 | 301 | 166780 | 17832 | 8229155 | 49835
2026-08-18 | planning | architecture docs (Da Vinci) |  |  | claude-opus-5-5 | claude-opus-5-5 | 81 | 562 | 262081 | 27177 | 12295498 | 70536
2026-08-19 | planning | UX design |  |  | claude-opus-5-5 | claude-opus-5-5 | 115 | 470 | 330666 | 40708 | 15363802 | 95045
2026-08-19 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 78 | 390 | 222864 | 26681 | 11598949 | 64642
2026-08-19 | planning | architecture docs (Da Vinci) |  |  | claude-opus-5-5 | claude-opus-5-5 | 60 | 321 | 226490 | 23132 | 9747865 | 59328
2026-08-20 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 106 | 560 | 297386 | 26906 | 13927722 | 76758
2026-08-20 | planning | architecture docs (Da Vinci) |  |  | claude-opus-5-5 | claude-opus-5-5 | 84 | 606 | 317527 | 35945 | 13770749 | 70015
2026-08-21 | planning | governance (Jules) |  |  | claude-opus-5-5 | claude-opus-5-5 | 97 | 419 | 251652 | 27593 | 12039647 | 77584
2026-08-21 | planning | architecture docs (Da Vinci) |  |  | claude-opus-5-5 | claude-opus-5-5 | 44 | 250 | 125295 | 14398 | 6108395 | 43922
2026-08-24 | planning | architecture docs (Da Vinci) |  |  | claude-opus-5-5 | claude-opus-5-5 | 100 | 565 | 315117 | 36459 | 14730425 | 93789
2026-08-24 | planning | epics & stories |  |  | claude-opus-5-5 | claude-opus-5-5 | 120 | 745 | 419296 | 52593 | 19827151 | 113428
2026-08-25 | planning | epics & stories |  |  | claude-opus-5-5 | claude-opus-5-5 | 164 | 1183 | 509645 | 54562 | 23821402 | 157684
2026-08-25 | story | PORTAL-111 | 2.5 | Payment creation with maker-checker approval and execution | claude-opus-5-5 | claude-opus-5-5 | 20 | 90 | 57544 | 6553 | 2710803 | 14873
2026-08-25 | story | PORTAL-114 | 3.2 | Outbox relay from the SQL ledger to Event Hubs | claude-opus-5-5 | claude-opus-5-5 | 10 | 72 | 31119 | 3700 | 1374125 | 8714
2026-08-25 | story | PORTAL-117 | 3.5 | Behind-the-scenes stage panel | claude-opus-5-5 | claude-opus-5-5 | 16 | 118 | 47657 | 5900 | 2104710 | 10964
2026-08-25 | story | PORTAL-119 | 4.2 | Cash forecast model tracked in MLflow and registered in Unity Catalog | claude-opus-5-5 | claude-opus-5-5 | 9 | 62 | 30854 | 3083 | 1403160 | 8503
2026-08-25 | story | PORTAL-121 | 4.4 | Batch scoring into forecasts and anomalies tables | claude-opus-5-5 | claude-opus-5-5 | 18 | 69 | 48045 | 6264 | 2478204 | 17017
2026-08-25 | story | PORTAL-123 | 5.1 | Region-2 AKS from the same Terraform module | claude-opus-5-5 | claude-opus-5-5 | 14 | 110 | 47293 | 6727 | 2257245 | 16564
2026-08-25 | story | PORTAL-124 | 5.2 | Front Door origins, health probes and Front Door-only ingress | claude-opus-5-5 | claude-opus-5-5 | 13 | 51 | 36120 | 4785 | 1590908 | 11049
2026-08-25 | story | PORTAL-126 | 5.4 | Grafana requests-per-second by region | claude-opus-5-5 | claude-opus-5-5 | 13 | 75 | 48527 | 5417 | 2117224 | 12626
2026-08-25 | story | PORTAL-127 | 5.5 | Regional failover drill and runbook | claude-opus-5-5 | claude-opus-5-5 | 14 | 134 | 48954 | 5608 | 2442046 | 14448
2026-08-25 | story | PORTAL-128 | 6.1 | Security controls evidence pack for the CISO review | claude-opus-5-5 | claude-opus-5-5 | 15 | 117 | 54291 | 6229 | 2641089 | 13996
2026-08-25 | story | PORTAL-131 | 6.4 | CAB approval, production cut-over and hypercare | claude-opus-5-5 | claude-opus-5-5 | 15 | 95 | 43160 | 4790 | 2214174 | 16918
2026-08-26 | planning | epics & stories |  |  | claude-opus-5-5 | claude-opus-5-5 | 182 | 849 | 546788 | 64133 | 25647872 | 130488
2026-08-26 | story | PORTAL-115 | 3.3 | Bronze ingestion from the Event Hubs Kafka endpoint | claude-opus-5-5 | claude-opus-5-5 | 16 | 106 | 46803 | 5534 | 2271940 | 15080
2026-08-26 | story | PORTAL-116 | 3.4 | Silver and gold Delta transforms with serving-schema write-back | claude-opus-5-5 | claude-opus-5-5 | 13 | 109 | 48679 | 5933 | 2293063 | 10145
2026-08-26 | story | PORTAL-120 | 4.3 | Isolation Forest payment anomaly detection | claude-opus-5-5 | claude-opus-5-5 | 19 | 94 | 57618 | 6622 | 2712777 | 14386
2026-08-26 | story | PORTAL-129 | 6.2 | PDPA data-protection assessment and penetration test remediation | claude-opus-5-5 | claude-opus-5-5 | 16 | 48 | 46669 | 4208 | 2028847 | 13387
2026-08-26 | story | PORTAL-130 | 6.3 | UAT with Group Treasury and business sign-off | claude-opus-5-5 | claude-opus-5-5 | 14 | 87 | 45760 | 5179 | 2082456 | 8342
2026-08-27 | planning | epics & stories |  |  | claude-opus-5-5 | claude-opus-5-5 | 123 | 871 | 360823 | 43843 | 17811235 | 108032
2026-08-27 | story | PORTAL-112 | 2.6 | Portal chrome: region badge, synthetic-data banner and error states | claude-opus-5-5 | claude-opus-5-5 | 16 | 79 | 51347 | 4158 | 2238077 | 14180
2026-08-27 | story | PORTAL-113 | 3.1 | Seeded synthetic world: companies, payroll cycles, suppliers and planted anomalies | claude-opus-5-5 | claude-opus-5-5 | 19 | 109 | 58655 | 5445 | 2606398 | 16111
2026-08-27 | story | PORTAL-118 | 4.1 | Unity Catalog lineage from gold back to the Event Hubs source | claude-opus-5-5 | claude-opus-5-5 | 11 | 86 | 41416 | 4593 | 1938969 | 10805
2026-08-27 | story | PORTAL-122 | 4.5 | Forecast screen and anomaly flags in the portal | claude-opus-5-5 | claude-opus-5-5 | 11 | 62 | 34832 | 3620 | 1689013 | 10153
2026-08-27 | story | PORTAL-125 | 5.3 | SQL failover group behind a Terraform flag | claude-opus-5-5 | claude-opus-5-5 | 15 | 79 | 51280 | 5066 | 2473649 | 12558
2026-08-31 | story | PORTAL-101 | 1.1 | Terraform resource groups and least-privilege Jenkins identity | claude-opus-5-5 | claude-opus-5-5 | 52 | 331 | 157862 | 18054 | 7801120 | 50356
2026-09-01 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 15 | 80 | 47584 | 5005 | 2013751 | 12114
2026-09-01 | story | PORTAL-101 | 1.1 | Terraform resource groups and least-privilege Jenkins identity | claude-opus-5-5 | claude-opus-5-5 | 75 | 458 | 252798 | 26459 | 11271879 | 66804
2026-09-02 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 11 | 55 | 42880 | 4882 | 1990420 | 13169
2026-09-02 | story | PORTAL-101 | 1.1 | Terraform resource groups and least-privilege Jenkins identity | claude-opus-5-5 | claude-opus-5-5 | 39 | 229 | 125457 | 13143 | 5596394 | 33558
2026-09-02 | story | PORTAL-102 | 1.2 | AKS with Node Auto Provisioning, Istio mTLS STRICT and Kong ingress | claude-opus-5-5 | claude-opus-5-5 | 75 | 466 | 232137 | 25565 | 10964653 | 59443
2026-09-03 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 11 | 66 | 35748 | 5243 | 1738363 | 9185
2026-09-03 | story | PORTAL-102 | 1.2 | AKS with Node Auto Provisioning, Istio mTLS STRICT and Kong ingress | claude-opus-5-5 | claude-opus-5-5 | 38 | 237 | 126654 | 13192 | 5697410 | 34467
2026-09-04 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 10 | 66 | 32926 | 3476 | 1655761 | 10556
2026-09-04 | story | PORTAL-102 | 1.2 | AKS with Node Auto Provisioning, Istio mTLS STRICT and Kong ingress | claude-opus-5-5 | claude-opus-5-5 | 71 | 437 | 226465 | 22539 | 10192270 | 61767
2026-09-07 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 14 | 72 | 41883 | 4807 | 2113125 | 12112
2026-09-07 | story | PORTAL-102 | 1.2 | AKS with Node Auto Provisioning, Istio mTLS STRICT and Kong ingress | claude-opus-5-5 | claude-opus-5-5 | 55 | 328 | 191155 | 21991 | 8414887 | 55135
2026-09-07 | story | PORTAL-103 | 1.3 | Vault with Key Vault auto-unseal and secret-free services | claude-opus-5-5 | claude-opus-5-5 | 39 | 241 | 114637 | 13263 | 5196583 | 28914
2026-09-08 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 11 | 48 | 32764 | 3855 | 1476670 | 8166
2026-09-08 | story | PORTAL-103 | 1.3 | Vault with Key Vault auto-unseal and secret-free services | claude-opus-5-5 | claude-opus-5-5 | 61 | 443 | 222188 | 25765 | 9679099 | 56700
2026-09-09 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 10 | 57 | 34357 | 4090 | 1546984 | 10219
2026-09-09 | story | PORTAL-103 | 1.3 | Vault with Key Vault auto-unseal and secret-free services | claude-opus-5-5 | claude-opus-5-5 | 67 | 271 | 202704 | 22565 | 9316496 | 58397
2026-09-09 | story | PORTAL-104 | 1.4 | Parallel microservice image builds with Kaniko on Jenkins agents | claude-opus-5-5 | claude-opus-5-5 | 44 | 169 | 113526 | 12988 | 5839754 | 32858
2026-09-10 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 10 | 65 | 27564 | 3196 | 1340571 | 7171
2026-09-10 | story | PORTAL-104 | 1.4 | Parallel microservice image builds with Kaniko on Jenkins agents | claude-opus-5-5 | claude-opus-5-5 | 31 | 235 | 102870 | 11693 | 4648758 | 26584
2026-09-11 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 6 | 34 | 19277 | 3032 | 1076327 | 6388
2026-09-11 | story | PORTAL-104 | 1.4 | Parallel microservice image builds with Kaniko on Jenkins agents | claude-opus-5-5 | claude-opus-5-5 | 64 | 303 | 194183 | 24258 | 9027955 | 54536
2026-09-11 | story | PORTAL-105 | 1.5 | Private endpoints and private DNS for lake, SQL, Key Vault and Event Hubs | claude-opus-5-5 | claude-opus-5-5 | 49 | 305 | 174986 | 21590 | 7586807 | 44178
2026-09-14 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 15 | 78 | 43878 | 3982 | 1897432 | 12561
2026-09-14 | story | PORTAL-105 | 1.5 | Private endpoints and private DNS for lake, SQL, Key Vault and Event Hubs | claude-opus-5-5 | claude-opus-5-5 | 33 | 176 | 91822 | 10313 | 4543714 | 24366
2026-09-15 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 11 | 47 | 34092 | 3576 | 1594796 | 9097
2026-09-15 | story | PORTAL-105 | 1.5 | Private endpoints and private DNS for lake, SQL, Key Vault and Event Hubs | claude-opus-5-5 | claude-opus-5-5 | 58 | 326 | 173804 | 18832 | 8595759 | 56718
2026-09-15 | story | PORTAL-106 | 1.6 | Cost guardrails: Databricks cluster policy and clean terraform destroy | claude-opus-5-5 | claude-opus-5-5 | 37 | 260 | 107895 | 11877 | 4948217 | 29551
2026-09-16 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 5 | 33 | 16927 | 2219 | 769659 | 4631
2026-09-16 | story | PORTAL-106 | 1.6 | Cost guardrails: Databricks cluster policy and clean terraform destroy | claude-opus-5-5 | claude-opus-5-5 | 45 | 222 | 120302 | 13976 | 6091433 | 33766
2026-09-17 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 14 | 107 | 44874 | 5273 | 1938427 | 10050
2026-09-17 | story | PORTAL-107 | 2.1 | Entra External ID sign-in and company-scoped sessions | claude-opus-5-5 | claude-opus-5-5 | 44 | 312 | 128971 | 14932 | 6288681 | 40508
2026-09-18 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 7 | 43 | 23296 | 2988 | 1042987 | 5174
2026-09-18 | story | PORTAL-107 | 2.1 | Entra External ID sign-in and company-scoped sessions | claude-opus-5-5 | claude-opus-5-5 | 69 | 481 | 211417 | 25722 | 10560405 | 62698
2026-09-21 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 9 | 45 | 31007 | 3778 | 1461821 | 8079
2026-09-21 | story | PORTAL-107 | 2.1 | Entra External ID sign-in and company-scoped sessions | claude-opus-5-5 | claude-opus-5-5 | 77 | 485 | 243384 | 30101 | 12062791 | 66635
2026-09-21 | story | PORTAL-108 | 2.2 | Row-level security for company isolation with blocked-access logging | claude-opus-5-5 | claude-opus-5-5 | 44 | 304 | 135137 | 15932 | 6496977 | 38883
2026-09-22 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 14 | 111 | 41047 | 5481 | 1997444 | 9986
2026-09-22 | story | PORTAL-108 | 2.2 | Row-level security for company isolation with blocked-access logging | claude-opus-5-5 | claude-opus-5-5 | 36 | 210 | 104405 | 12395 | 4780417 | 30800
2026-09-23 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 9 | 65 | 32499 | 3303 | 1472429 | 8022
2026-09-23 | story | PORTAL-108 | 2.2 | Row-level security for company isolation with blocked-access logging | claude-opus-5-5 | claude-opus-5-5 | 53 | 278 | 144969 | 15749 | 6603437 | 41995
2026-09-24 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 9 | 66 | 31602 | 3911 | 1544452 | 10963
2026-09-24 | story | PORTAL-108 | 2.2 | Row-level security for company isolation with blocked-access logging | claude-opus-5-5 | claude-opus-5-5 | 45 | 297 | 144081 | 16395 | 6667936 | 45700
2026-09-24 | story | PORTAL-109 | 2.3 | Cash position and liquidity dashboard from the serving schema | claude-opus-5-5 | claude-opus-5-5 | 58 | 257 | 173624 | 16130 | 8384494 | 50071
2026-09-25 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 10 | 68 | 32174 | 3343 | 1531137 | 7254
2026-09-25 | story | PORTAL-109 | 2.3 | Cash position and liquidity dashboard from the serving schema | claude-opus-5-5 | claude-opus-5-5 | 53 | 379 | 167224 | 19525 | 7911773 | 49126
2026-09-28 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 9 | 30 | 31328 | 3021 | 1385585 | 7209
2026-09-28 | story | PORTAL-109 | 2.3 | Cash position and liquidity dashboard from the serving schema | claude-opus-5-5 | claude-opus-5-5 | 37 | 282 | 123020 | 13397 | 5851398 | 36902
2026-09-28 | story | PORTAL-110 | 2.4 | Accounts, balances and transactions | claude-opus-5-5 | claude-opus-5-5 | 29 | 186 | 101378 | 10934 | 4819365 | 26083
2026-09-29 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 13 | 72 | 42645 | 4544 | 1774515 | 11029
2026-09-29 | story | PORTAL-110 | 2.4 | Accounts, balances and transactions | claude-opus-5-5 | claude-opus-5-5 | 30 | 137 | 100434 | 11537 | 4767173 | 27348
2026-09-30 | ops | merges, promotions & deploys |  |  | claude-opus-5-5 | claude-opus-5-5 | 9 | 64 | 29110 | 3215 | 1270343 | 7615
2026-09-30 | story | PORTAL-110 | 2.4 | Accounts, balances and transactions | claude-opus-5-5 | claude-opus-5-5 | 31 | 176 | 88977 | 11904 | 4446821 | 26254

## Project Timeline
Project timeline
Started 2026-07-27; still running; calendar days, 48 working days. From git history of the BMad artifacts and sprint status, the agents' sanctums and the token ledger.
Category | Name | Detail | Status | Started | Completed | Days | Source
project | corportal | 48 working days | in progress | 2026-07-27 |  |  | summary
bmad stage | spec / PRD | _bmad-output/specs/spec-corporate-portal-poc/SPEC.md |  | 2026-07-29 | 2026-08-04 | 7 | synthetic
bmad stage | architecture | _bmad-output/specs/spec-corporate-portal-poc/architecture-diagrams.md |  | 2026-08-05 | 2026-08-14 | 10 | synthetic
bmad stage | UX design | _bmad-output/planning-artifacts/ux-designs/ux-corportal-2026-09-30/EXPERIENCE.md |  | 2026-08-10 | 2026-08-19 | 10 | synthetic
bmad stage | epics & stories | docs/costing/corportal-portfolio.estimate.json |  | 2026-08-24 | 2026-08-27 | 4 | synthetic
bmad stage | sprint status | docs/costing/portfolio-ledger/project_timeline.csv |  | 2026-08-31 | 2026-09-30 | 31 | synthetic
agent | agent-jules | 5 session logs |  | 2026-08-17 | 2026-08-21 | 5 | synthetic
agent | agent-davinci | 4 session logs |  | 2026-08-18 | 2026-08-24 | 7 | synthetic
agent | agent-scrooge | 6 session logs |  | 2026-08-24 | 2026-09-30 | 38 | synthetic
epic | epic-1 | 6 stories | done | 2026-08-31 | 2026-09-16 | 17 | synthetic
story | 1-1-terraform-resource-groups-and | epic-1 | done | 2026-08-31 | 2026-09-02 | 3 | synthetic
story | 1-2-aks-with-node-auto | epic-1 | done | 2026-09-02 | 2026-09-07 | 6 | synthetic
story | 1-3-vault-with-key-vault | epic-1 | done | 2026-09-07 | 2026-09-09 | 3 | synthetic
story | 1-4-parallel-microservice-image-builds | epic-1 | done | 2026-09-09 | 2026-09-11 | 3 | synthetic
story | 1-5-private-endpoints-and-private | epic-1 | done | 2026-09-11 | 2026-09-15 | 5 | synthetic
story | 1-6-cost-guardrails-databricks-cluster | epic-1 | done | 2026-09-15 | 2026-09-16 | 2 | synthetic
epic | epic-2 | 6 stories | in-progress | 2026-09-17 |  |  | synthetic
story | 2-1-entra-external-id-sign-in | epic-2 | done | 2026-09-17 | 2026-09-21 | 5 | synthetic
story | 2-2-row-level-security-for-company | epic-2 | done | 2026-09-21 | 2026-09-24 | 4 | synthetic
story | 2-3-cash-position-and-liquidity | epic-2 | done | 2026-09-24 | 2026-09-28 | 5 | synthetic
story | 2-4-accounts-balances-and-transactions | epic-2 | in-progress | 2026-09-28 |  |  | synthetic
story | 2-5-payment-creation-with-maker-checker | epic-2 | backlog |  |  |  | synthetic
story | 2-6-portal-chrome-region-badge | epic-2 | backlog |  |  |  | synthetic
epic | epic-3 | 5 stories | backlog |  |  |  | synthetic
story | 3-1-seeded-synthetic-world-companies | epic-3 | backlog |  |  |  | synthetic
story | 3-2-outbox-relay-from-the | epic-3 | backlog |  |  |  | synthetic
story | 3-3-bronze-ingestion-from-the | epic-3 | backlog |  |  |  | synthetic
story | 3-4-silver-and-gold-delta | epic-3 | backlog |  |  |  | synthetic
story | 3-5-behind-the-scenes-stage-panel | epic-3 | backlog |  |  |  | synthetic
epic | epic-4 | 5 stories | backlog |  |  |  | synthetic
story | 4-1-unity-catalog-lineage-from | epic-4 | backlog |  |  |  | synthetic
story | 4-2-cash-forecast-model-tracked | epic-4 | backlog |  |  |  | synthetic
story | 4-3-isolation-forest-payment-anomaly | epic-4 | backlog |  |  |  | synthetic
story | 4-4-batch-scoring-into-forecasts | epic-4 | backlog |  |  |  | synthetic
story | 4-5-forecast-screen-and-anomaly | epic-4 | backlog |  |  |  | synthetic
epic | epic-5 | 5 stories | backlog |  |  |  | synthetic
story | 5-1-region-2-aks-from-the | epic-5 | backlog |  |  |  | synthetic
story | 5-2-front-door-origins-health | epic-5 | backlog |  |  |  | synthetic
story | 5-3-sql-failover-group-behind | epic-5 | backlog |  |  |  | synthetic
story | 5-4-grafana-requests-per-second-by-region | epic-5 | backlog |  |  |  | synthetic
story | 5-5-regional-failover-drill-and | epic-5 | backlog |  |  |  | synthetic
epic | epic-6 | 4 stories | backlog |  |  |  | synthetic
story | 6-1-security-controls-evidence-pack | epic-6 | backlog |  |  |  | synthetic
story | 6-2-pdpa-data-protection-assessment-and | epic-6 | backlog |  |  |  | synthetic
story | 6-3-uat-with-group-treasury | epic-6 | backlog |  |  |  | synthetic
story | 6-4-cab-approval-production-cut-over | epic-6 | backlog |  |  |  | synthetic
claude | brainstorming | planning |  | 2026-07-27 | 2026-07-28 | 2 | token ledger
claude | spec | planning |  | 2026-07-29 | 2026-08-04 | 7 | token ledger
claude | architecture | planning |  | 2026-08-05 | 2026-08-14 | 10 | token ledger
claude | UX design | planning |  | 2026-08-10 | 2026-08-19 | 10 | token ledger
claude | governance (Jules) | planning |  | 2026-08-17 | 2026-08-21 | 5 | token ledger
claude | architecture docs (Da Vinci) | planning |  | 2026-08-18 | 2026-08-24 | 7 | token ledger
claude | epics & stories | planning |  | 2026-08-24 | 2026-08-27 | 4 | token ledger
claude | merges, promotions & deploys | ops |  | 2026-09-01 | 2026-09-30 | 30 | token ledger
claude | PORTAL-101 | story |  | 2026-08-31 | 2026-09-02 | 3 | token ledger
claude | PORTAL-102 | story |  | 2026-09-02 | 2026-09-07 | 6 | token ledger
claude | PORTAL-103 | story |  | 2026-09-07 | 2026-09-09 | 3 | token ledger
claude | PORTAL-104 | story |  | 2026-09-09 | 2026-09-11 | 3 | token ledger
claude | PORTAL-105 | story |  | 2026-09-11 | 2026-09-15 | 5 | token ledger
claude | PORTAL-106 | story |  | 2026-09-15 | 2026-09-16 | 2 | token ledger
claude | PORTAL-107 | story |  | 2026-09-17 | 2026-09-21 | 5 | token ledger
claude | PORTAL-108 | story |  | 2026-09-21 | 2026-09-24 | 4 | token ledger
claude | PORTAL-109 | story |  | 2026-09-24 | 2026-09-28 | 5 | token ledger
claude | PORTAL-110 | story |  | 2026-09-28 | 2026-09-30 | 3 | token ledger
claude | PORTAL-111 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-112 | story |  | 2026-08-27 | 2026-08-27 | 1 | token ledger
claude | PORTAL-113 | story |  | 2026-08-27 | 2026-08-27 | 1 | token ledger
claude | PORTAL-114 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-115 | story |  | 2026-08-26 | 2026-08-26 | 1 | token ledger
claude | PORTAL-116 | story |  | 2026-08-26 | 2026-08-26 | 1 | token ledger
claude | PORTAL-117 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-118 | story |  | 2026-08-27 | 2026-08-27 | 1 | token ledger
claude | PORTAL-119 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-120 | story |  | 2026-08-26 | 2026-08-26 | 1 | token ledger
claude | PORTAL-121 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-122 | story |  | 2026-08-27 | 2026-08-27 | 1 | token ledger
claude | PORTAL-123 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-124 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-125 | story |  | 2026-08-27 | 2026-08-27 | 1 | token ledger
claude | PORTAL-126 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-127 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-128 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger
claude | PORTAL-129 | story |  | 2026-08-26 | 2026-08-26 | 1 | token ledger
claude | PORTAL-130 | story |  | 2026-08-26 | 2026-08-26 | 1 | token ledger
claude | PORTAL-131 | story |  | 2026-08-25 | 2026-08-25 | 1 | token ledger

## AI Feedback
AI feedback by epic
The team's rating of the AI at the end of each epic, 1 (very poor) to 5 (excellent), and what went wrong when it was poor (1 or 2). From ai-feedback.csv in Scrooge's sanctum.
Epic | Rating | Poor | Categories | Other | Comment | Status | Recorded
epic-1 | 4 | no |  |  | Terraform and Istio landed fast; the Kong token plugin needed two rework rounds | rated | 2026-09-17
Average

## Sources & Gaps
Sources, assumptions and gaps
Price basis
Azure Retail Prices API list prices (pay-as-you-go, no discounts), region westus3, USD, fetched 2026-09-30.
Rate card: owner, 2026-09-28 (blended average day rate per person), updated 2026-09-30.
Claude API list prices from https://platform.claude.com/docs/en/about-claude/pricing, read 2026-09-28, USD per million tokens. Claude Code on a subscription is billed per seat: this is the API-equivalent cost.
Horizon: 3 years of run after go-live, run costs rising 3% a year.
Gaps: not priced and not in any total
All client, user, team, calendar, epic and Claude-usage figures are synthetic portfolio figures (owner request 2026-09-30); the SPEC is a PoC for a 3-day demo.
No epics file exists: the 6 epics and 31 stories were derived from the SPEC capabilities (CAP-1 to CAP-15) and live only in this model.
No real Claude ledger: usage in docs/costing/portfolio-ledger/ is synthesised (Opus 5.5, planning before 2026-08-31, stories inside their epic windows); not-started stories carry only their drafting calls from the epics & stories phase.
Environments Dev, Test, UAT and Prod are the owner's rule for this project (2026-09-30); the SPEC itself describes one PoC environment destroyed after the demo.
Regions follow SPEC/stack.md (West US 3 primary, North Central US secondary, chosen as the cheapest AKS regions); Sentral's PDPA cross-border transfer review and BNM RMiT may move production to Malaysia West, which would reprice every line.
Existing Jenkins VM and container registry are not priced (stack.md: existing assets).
Entra External ID: assumed within the free 50,000 MAU tier for ~6,500 registered users; not priced.
HashiCorp Vault Community (BSL), Kong OSS, Prometheus and Grafana: no licence cost assumed (SPEC assumption).
Databricks DBU rate assumed at 1 DBU per D4s_v5 node-hour; confirm against the workspace's VM DBU table.
Revenue: none given, so no payback or return on cost.
Actual cloud spend: no Azure Cost Management export for Sentral's subscription.
Revenue: none given, so the Multi-Year sheet shows costs only.
Assumptions and owner statements (not from the BMad artifacts)
UAT / Log Analytics ingestion: assumption: AKS and SQL diagnostics, ~15 GB a month billed; synthetic portfolio figure, owner request 2026-09-30
Prod / Log Analytics ingestion: assumption: AKS, SQL, Front Door and audit diagnostics, ~60 GB a month billed; synthetic portfolio figure, owner request 2026-09-30
Team / Delivery lead: assumption: AI-assisted delivery team for 31 stories over 75 working days; synthetic portfolio figure, owner request 2026-09-30
Team / Solution architect: assumption: AI-assisted delivery team for 31 stories over 75 working days; synthetic portfolio figure, owner request 2026-09-30
Team / QA engineer: assumption: AI-assisted delivery team for 31 stories over 75 working days; synthetic portfolio figure, owner request 2026-09-30
Other / Penetration test (external CREST tester): assumption: pre-go-live pen test required by Sentral's Group Security; synthetic portfolio figure, owner request 2026-09-30
Other / PDPA data-protection impact assessment: assumption: external privacy counsel for PDPA 2010 and cross-border transfer; synthetic portfolio figure, owner request 2026-09-30
Run cost / Annual penetration test: assumption: Sentral Group Security policy, yearly retest; synthetic portfolio figure, owner request 2026-09-30
Support / Support engineer: assumption: L2 support, patching and on-call for the portal; synthetic portfolio figure, owner request 2026-09-30
Support / Cloud / DevOps engineer: assumption: AKS, Istio, Kong and Vault upgrades in two regions; synthetic portfolio figure, owner request 2026-09-30
Support / Data engineer: assumption: pipeline care and model retraining; synthetic portfolio figure, owner request 2026-09-30
Phase budget / brainstorming: assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Phase budget / spec: assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Phase budget / architecture: assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Phase budget / UX design: assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Phase budget / governance (Jules): assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Phase budget / architecture docs (Da Vinci): assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Phase budget / epics & stories: assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Phase budget / merges, promotions & deploys: assumption: owner's Claude API budget per phase; synthetic portfolio figure, owner request 2026-09-30
Stamp: built 2026-09-30T15:05:25; sha256 of each cited file
_bmad-output/specs/spec-corporate-portal-poc/SPEC.md ccaff96ab2db
_bmad-output/specs/spec-corporate-portal-poc/stack.md e93f379b585d
docs/costing/portfolio-ledger/claude_usage.csv 3363442b9189
docs/costing/portfolio-ledger/claude-prices.json 0dcde61aa110
docs/costing/portfolio-ledger/project_timeline.csv 17cb7fd9e318
docs/costing/portfolio-ledger/claude_usage_daily.csv 4dcfb5327e2b
docs/costing/portfolio-ledger/ai-feedback.csv 72619fa788a6